## 2024 Status of Recommendations
Status of Audit Recommendations by the Office of the D.C. Auditor, as of December 31, 2023. Recommendations that are shaded were sent to all identified agencies for a response, but are only listed once in this chart. For best results filter by Report Title or Agency or Status.
Report Title | Rec. No. | Recommendation | Agency | Status | Notes
Improvements to School Modernization Contract Administration Could Save District Money (October 19, 2020) (Review of the Eliot-HIne Middle School Modernization project, also see Eliot-Hine Middle School Modernization Project Closeout Report issued January 18, 2022) | 1 | During final project accounting and closeout, we recommend DGS require the CM to provide the listing of subcontractors covered by the SDI policy and the amounts being covered for each subcontractor. | DGS | In progress
Improvements to School Modernization Contract Administration Could Save District Money (October 19, 2020) (Review of the Eliot-HIne Middle School Modernization project, also see Eliot-Hine Middle School Modernization Project Closeout Report issued January 18, 2022) | 3 | We recommend DGS incorporate steps to perform a reconciliation of the craft labor costs submitted with the pay applications and the certified payroll records. This can be achieved through a sampling process or through examination of the full population of labor costs and certified payroll documents. | DGS | In progress
Improvements to School Modernization Contract Administration Could Save District Money (October 19, 2020) (Review of the Eliot-HIne Middle School Modernization project, also see Eliot-Hine Middle School Modernization Project Closeout Report issued January 18, 2022) | 5 | For future projects, DGS [should] include contract language to better define composition of "fully burdened" staff rates, and to delineate between fringe costs allowed as a cost of work versus those considered disallowed. | DGS | In progress
Improvements to School Modernization Contract Administration Could Save District Money (October 19, 2020) (Review of the Eliot-HIne Middle School Modernization project, also see Eliot-Hine Middle School Modernization Project Closeout Report issued January 18, 2022) | 6 | The Department of Employment Services (DOES) should verify DGS's reconciliation of local labor at the end of the project to validate the workforce achieved 51% of local labor. | DGS | In progress
Improvements to School Modernization Contract Administration Could Save District Money (October 19, 2020) (Review of the Eliot-HIne Middle School Modernization project, also see Eliot-Hine Middle School Modernization Project Closeout Report issued January 18, 2022) | 6 |  | DOES
Improvements to School Modernization Contract Administration Could Save District Money (October 19, 2020) (Review of the Eliot-HIne Middle School Modernization project, also see Eliot-Hine Middle School Modernization Project Closeout Report issued January 18, 2022) | 7 | During the final reconciliation, DGS [should] validate that the contingency transferred for use was fully billed, or identify opportunities for additional savings where the CM did not use all the contingency approved. | DGS | Implemented
More Urgency Needed to Fix Lead-Based Paint Hazards (November 18, 2020) | 3 | DCHA should comply with Lead Safe Housing Rule (LSHR) requirement to stabilize any reported deteriorated paint within 30 days, document use of lead safe work practices, and supply clearance reports when required. | DCHA | Implemented
More Urgency Needed to Fix Lead-Based Paint Hazards (November 18, 2020) | 4 | The DCHA Property Management Office should develop and implement a plan to reduce the backlog of work orders, including work orders related to lead-based paint. | DCHA | Implemented
More Urgency Needed to Fix Lead-Based Paint Hazards (November 18, 2020) | 5 | The DCHA Property Management Office should develop comprehensive internal policies and procedures for the work order process, including a requirement to maintain all work order related documentation, from DCHA-managed properties and privately managed properties in a centralized location. | DCHA | In progress | DCHA reported this as being implemented and referenced sections of the agency Policy and Procedure Manual, however specific information regarding privately managed properties in a centralized location was not included.
More Urgency Needed to Fix Lead-Based Paint Hazards (November 18, 2020) | 6 | DCHA Property Management Operations (PMO) should enforce Lead Safe Housing Rule (24 CFR 35 Section 35.1355 (a)(2)) requirements to conduct visual assessments every 12 months. | DCHA | In progress | DCHA reported this as being Implemented, and progress has been made however we did not see proof of enforcement of this requirement.
More Urgency Needed to Fix Lead-Based Paint Hazards (November 18, 2020) | 8 | The DCHA Office of Audit and Compliance (OAC) should implement a quality control process for inspections conducted by Property Management Operations (PMO) for compliance with the Lead Safe Housing Rule, 24 CFR Part 35.1355 (a)(2). | DCHA | In progress | DCHA reported this as being implemented however a quality control process to ensure inspections are being conducted properly is not apparent.
More Urgency Needed to Fix Lead-Based Paint Hazards (November 18, 2020) | 9 | DOEE should continue to advocate for the D.C. Council to expand the definition of “owner” to include the District government and its independent agencies like DCHA within its enforcement powers. | DOEE | No action intended - management accepts risk | DOEE has been discussing with the Council, but previous bills introduced were not enacted and there is no legislation before the Council at this time.
More Urgency Needed to Fix Lead-Based Paint Hazards (November 18, 2020) | 11 | DOEE should establish deadlines for each step and team involved in the enforcement process and add an indicator to the PAR that gives information on the percentage of cases in which lead hazards are remediated in a given amount of time. | DOEE | No action intended - management accepts risk | As previously reported, DOEE has implemented this recommendation with the exception of adding an indicator to the performance and accountability reporting (PAR).
More Urgency Needed to Fix Lead-Based Paint Hazards (November 18, 2020) | 14 | DOEE should use additional authority granted in the law to include remediating lead hazards and issuing a lien on the owner’s property, denying rental permits to owners to ensure lead hazards are remediated, issuing multiday fines, and collaborating with other agencies as needed to use this authority. DOEE should establish internal policies as necessary guiding how and when this authority will be applied. | DOEE | No action intended - management accepts risk | This recommendation was previously reported as In progress. Efforts by DOEE to work with DCLP have not resulted in an arrangement for rental permits to be denied if and when warranted.
D.C. Lacked Unified System to Track, Reduce Settlements & Judgments (December 7, 2020) | 1 | The Executive should ensure that ORM has the support, resources, and data system(s) needed to identify, analyze, and prioritize S&Js and risks throughout District government including policies and procedures requiring all executive branch agencies to timely report their settlements and judgements to ORM and to use standard terms to describe claim types. This also will allow the Executive to meet the statutory requirement to present a settlements report to Congress. | EOM (ORM) | In progress
| 5 | ORM should collect and assess comprehensive S&J information for risk mitigation by agencies and present the annual risk report to the D.C. Council. ORM should use existing information systems to support risk assessments until its new enterprise risk management system (ERisk) S&J component is online. As ORM implements ERisk, it should ensure that all agencies are reporting all S&Js within ERisk regularly by conducting reconciliations to the District's financial system and other monitoring activities. | ORM | In progress
| 6 | ORM, OCFO, and OAG should jointly implement SOPs with clear agency responsibilities as needed to govern the processing, handling, and reporting of S&Js from the S&J Fund to facilitate compliance with the statutory requirements of D.C. Code § 2-402 and strengthen critical information sharing. This includes procedures for reclassifying expenditures when the S&J Fund is used for unanticipated expenditures. | ORM | In progress | OCFO reported this as ongoing, however ODCA has determined it to be In progress.
| 6 |  | OCFO |  | OCFO reported this as ongoing, however ODCA has determined it to be In progress.
| 6 |  | OAG |  | OCFO reported this as ongoing, however ODCA has determined it to be In progress.
Measuring What Matters: More and Better Data Needed to Improve D.C. Public Schools (March 10, 2021) | 1 | OSSE should * Review compliance with federal and District law on data collection and reporting with specific attention to data collections on discipline and attendance related to the federal Individuals with Disabilities Education Act, the District’s Student Fair Access to School Act, the School Attendance Clarification Amendment Act, and * Issue a data privacy policy to ensure compliance with the Family Educational Right to Privacy Act. | OSSE | Implemented | OSSE's move to automated submission of discipline data by Charters appears to have improved consistency of data collection from all LEAs.
Measuring What Matters: More and Better Data Needed to Improve D.C. Public Schools (March 10, 2021) | 2 | OSSE should create and implement a quality control process to ensure the integrity of education data. | OSSE | In progress | OSSE continues to improve the quality and clarity of the context and caveats it provides about the agency's analysis and reporting.
Measuring What Matters: More and Better Data Needed to Improve D.C. Public Schools (March 10, 2021) | 3 | OSSE should provide clear explanations of data limitations in current state education reports to provide full transparency until data integrity is improved and assured. | OSSE | In progress | OSSE continues to improve the quality and clarity of the context and caveats it provides about the agency's analysis and reporting.
Measuring What Matters: More and Better Data Needed to Improve D.C. Public Schools (March 10, 2021) | 4 | The D.C. Council enact legislation requiring the District to collect data included in the US Department of Education’s definition of a student longitudinal data system (student demographics, student special programs, student assessments, student enrollment: school entry and exit, student enrollment: school program type, student attendance, student discipline, student supports (i.e., school climate surveys), student courses, student-teacher links, teacher/Staff FTE, role, school, teacher demographics, teacher qualifications, teacher personnel (mobility, salary, etc.), data beyond enrollment for PreK, CTE, Adult Ed, postsecondary data, workforce data). | DC Council | Not yet started | The COW noted legislation was passed to authorize but not require the Deputy Mayor for Education to begin collecting data linking education and workforce outcomes.
Measuring What Matters: More and Better Data Needed to Improve D.C. Public Schools (March 10, 2021) | 5 | The D.C. Council enact legislation that requires data governance and stakeholder engagement practices to help assure the District’s education data system is successful and sustainable. | DC Council | Not yet started
Measuring What Matters: More and Better Data Needed to Improve D.C. Public Schools (March 10, 2021) | 6 | The D.C. Council enact legislation to provide for regular monitoring and reports on each step to ensure success. | DC Council | Not yet started
The Metropolitan Police Department and the Use of Deadly Force: Four Case Studies 2018-2019 (March 23, 2021) | 7 | MPD Should Release IAD's Final Investigative Report and the UFRB's Conclusions to the Public. | MPD | Implemented** | As noted, MPD has discontinued publishing the summary reports.
The Metropolitan Police Department and the Use of Deadly Force: Four Case Studies 2018-2019 (March 23, 2021) | 26 | MPD should ensure that all officers are adequately trained on how to use the ballistic shield, including how the deploying officer is to handle his pistol while holding the shield and the tactical formations to be employed when a shield is being used. | MPD | In progress | MPD anticipates training will be completed before the end of 2023.
The Metropolitan Police Department and the Use of Deadly Force: Four Case Studies 2018-2019 (March 23, 2021) | 27 | MPD should review training on how to breach a door, including training on when and how to do so, and the proper equipment to use. Training should be provided on each relevant breaching device available to the officer before the officer is authorized to use it. | MPD | In progress | MPD anticipates training will be completed before the end of 2023.
The Metropolitan Police Department and the Use of Deadly Force: Four Case Studies 2018-2019 (March 23, 2021) | 28 | MPD should provide and reinforce tactical training at regular intervals to relevant MPD personnel on how to approach a location where entry is contemplated and there is indication that an armed subject is within the premises to be entered. The training should address being in the line of fire, stacking, the "fatal Funnel," and seeking cover. | MPD | In progress | MPD anticipates training will be completed before the end of 2023.
Weakness Cited in Monitoring Lottery Contract CBEs (July 7, 2021) | 1 | The D.C Council should amend the law to clearly define "managerial functions" and "independently controlled owned and operated" with language that is measurable and verifiable. | DC Council | Not yet started | The Committee anticipates introducing legislation in 2024.
Weakness Cited in Monitoring Lottery Contract CBEs (July 7, 2021) | 2 | DSLBD should clearly identify in DCMR and SOPs how each relevant section of the D.C. Code is examined and reviewed and what supporting documentation is necessary to determine if the business meets the criteria for certification. | DSLBD | Implemented
Weakness Cited in Monitoring Lottery Contract CBEs (July 7, 2021) | 4 | The D.C. Council should amend the D.C. Code to clearly state what is required when reporting a material change. | DC Council | Not yet started | The Committee anticipates introducing legislation in 2024.
Weakness Cited in Monitoring Lottery Contract CBEs (July 7, 2021) | 5 | DSLBD should clearly identify in the DCMR what is required for recertification if the business has a material change to report. | DSLBD | Implemented
Weakness Cited in Monitoring Lottery Contract CBEs (July 7, 2021) | 6 | The D.C. Council should amend the law to delineate the responsibility of the contracting agency and the responsibility of DSLBD to ensure CBEs are performing the work. | DC Council | Not yet started | The Committee anticipates introducing legislation in 2024.
Weakness Cited in Monitoring Lottery Contract CBEs (July 7, 2021) | 7 | DSLBD should update the DCMR and finalize their Compliance Division SOPs to include responsibilities for reviewing and monitoring CBE participation on D.C. government contracts. | DSLBD | Implemented
Weakness Cited in Monitoring Lottery Contract CBEs (July 7, 2021) | 9 | OLG should comply with contract terms and the appointment of duties memo from the CO to the COTR and not approve invoices without supporting documentation for all work performed, including work performed by CBEs. | OLG | No action intended - management accepts risk | ODCA previously reported this recommendation as In progress, and OLG does receive some back up documentation with invoices. OLG disagrees with the recommendation that they should review all CBE subcontractor invoices.
DCPS Failed to Effectively Monitor Title I Contract (July 14, 2021) | 1 | DCPS should develop policies and procedures to ensure information provided in proposals is accurate by verifying it through external sources. | DCPS | In progress
DCPS Failed to Effectively Monitor Title I Contract (July 14, 2021) | 3 | DCPS should ensure that equipment purchases are supported by invoices and reported on equipment logs. Equipment logs should be reconciled periodically. | DCPS | Implemented
DCPS Failed to Effectively Monitor Title I Contract (July 14, 2021) | 4 | DCPS should develop policies and procedures (SOPs) to ensure contracted Title I teachers obtain cleared criminal background checks prior to, and throughout the duration of, issuing direct educational services. | DCPS | No longer applicable | According to DCPS this recommendation is Implemented, but notes they are no longer contracting a third-party vendor, so ODCA has determined this recommendation to be No longer applicable.
DCPS Failed to Effectively Monitor Title I Contract (July 14, 2021) | 6 | DCPS should include a CBE checkbox in its correspondence to the contractor, as well as its renewal policies, to ensure that the contractor is an active CBE or the contractor is going to subcontract to an active CBE, and then follow-up with monitoring and verification. | DCPS | Not yet started | DCPS reported this recommendation as In progress and indicated they will update the renewal notice letters to include the CBE/ subcontractor checkbox and will include the process for monitoring and verification before initial award and option year renewals in their SOPs. ODCA believes this recommendation is Not yet started.
DCPS Failed to Effectively Monitor Title I Contract (July 14, 2021) | 7 | DCPS's contract administrator should regularly monitor compliance with the First Source program to ensure the contractor complies with the 51% requirement by the end of the contract term. | DCPS | Not yet started | DCPS reported they are updating the Contract Administrator (CA) delegation letter to incorporate this task as part of the CA duties, however ODCA believes this recommendation is Not yet started.
Fiscal Year 2019 Annual Report on Advisory Neighborhood Commissions (August 9, 2021) | 2 | The OANC should continue to work with ANCs to strengthen compliance with internal control procedures to protect ANC assets and District resources, which can also improve accountability and public trust. | OANC | Implemented
National COVID-19 Data Quality Audit: District of Columbia (August 16, 2021) | 2 | The Mayor should initiate a comprehensive review of the COVID-19 pandemic response culminating in a public report with DC Health, OCME, HSEMA, and any other key agencies to determine what worked and what should be done differently in the face of a similar health emergency including any recommended updates to the District's Emergency Response Plan. | EOM (OCA) | In progress
District of Columbia 2020 Election Administration (November 16, 2021) | 1 | DCBOE should be coordinating with the DC Council to ensure that its overall funding, from both District and federal resources, covers its full mission. DCBOE should consider how it can demonstrate the impact of both its federal and local—including evidence-based reporting—as part of its efforts to ensure its operations have the resources they need to succeed. | DCBOE | Implemented
Eliot-Hine Middle School Modernization Construction Closeout Report (January 18, 2022) (Follow up to Improvements to School Modernization Contract Administration Could Save District Money issued October 19, 2020) | 1 | For future projects, we recommend DGS include contract language to specify only SDI costs solely related to the project, or costs for enrolled subcontractors only, may be allowable. The contract language should also specify the actual costs are subject to audit review. In cases where DGS agrees to a rate to be applied to enrolled subcontractors, DGS should obtain evidence from the CM during the GMP development to validate the rate is reflective of actual costs. | DGS | In progress
Eliot-Hine Middle School Modernization Construction Closeout Report (January 18, 2022) (Follow up to Improvements to School Modernization Contract Administration Could Save District Money issued October 19, 2020) | 2 | For future projects, we recommend DGS include contract language to better define composition of "fully burdened" staff rates, and to delineate between fringe costs allowed as a cost of work versus those considered disallowed. | DGS | In progress
Eliot-Hine Middle School Modernization Construction Closeout Report (January 18, 2022) (Follow up to Improvements to School Modernization Contract Administration Could Save District Money issued October 19, 2020) | 3 | We recommend DSLBD and DGS confirm the appropriate records are received from the respective CM or subcontractor as documents are processed, to confirm completeness of project records.* | DSLBD | Not yet started | DGS has indicated they will coordinate with DSLBD on confirmation of appropriate records.
Eliot-Hine Middle School Modernization Construction Closeout Report (January 18, 2022) (Follow up to Improvements to School Modernization Contract Administration Could Save District Money issued October 19, 2020) | 3 |  | DGS |  | DGS has indicated they will coordinate with DSLBD on confirmation of appropriate records.
Eliot-Hine Middle School Modernization Construction Closeout Report (January 18, 2022) (Follow up to Improvements to School Modernization Contract Administration Could Save District Money issued October 19, 2020) | 4 | For future projects, we recommend DGS modify the contract language so elements of Volume are not also calculated on the Volume total. | DGS | In progress
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 1 | OCF should develop standard operating procedures for the Fair Elections Program Division to track campaign committees referred for non-compliance and to document all steps in the process. | OCF | In progress | OCF reported this recommendation as Implemented but also noted revisions to the Fair Elections Program Standard Operating Procedures would be made. We have marked this as In Progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 2 | OCF should calculate the maximum matching amount using a separate process from the estimation used for the budget. OCF should use expenditures as defined by statute to calculate the maximum matching amount and assign another staff person to review the calculation to ensure accuracy. | OCF | In progress | OCF reported this recommendation as Implemented, and also noted changes to the D.C. Code (effective in November, 2021) to clarify base amount payments and the calculation for matching payments. We believe this is In progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 3 | OCF should reconcile reports of actual payments from OFRM with its payment records and campaign committee bank account records frequently enough to detect payments to the wrong campaign committee during the election cycle. | OCF | In progress | OCF reported this recommendation as Implemented. ODCA asked for a copy of the updated SOPs, but has not heard back, so we have marked this as In progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 4 | OCF should conduct a risk assessment for the Fair Elections Program e-filing system, determine which information is sensitive, and develop a written security plan to keep it safe. | OCF | In progress | OCF reported this recommendation as Implemented. ODCA asked for a copy of the updated SOPs, but has not heard back, so we have marked this as In progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 5 | When the nominating petition for a Fair Elections Program candidate is challenged, OCF should obtain and review the official Board of Elections order granting ballot access before authorizing the final base amount payment to the candidate’s campaign committee. | OCF | In progress | OCF reported this recommendation as Implemented. ODCA asked for a copy of the updated SOPs but has not heard back so we marked this as In progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 6 | OCF should develop standard operating procedures for auditors to determine if a second contribution from the same contributor to the same campaign committee exceeds the per-contributor limits or if it can be approved for matching because the campaign committee refunded previous contributions and remitted any matching payments for them. | OCF | In progress | OCF reported this recommendation as Implemented. ODCA asked for a copy of the updated SOPs but has not heard back so we marked this as In progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 7 | OCF should add to the e-filing system any additional documentation it receives from the campaign committee that justifies changing the status of a contribution from declined to approved. | OCF | In progress | OCF reported this recommendation as Implemented. ODCA asked for additional information but has not heard back so we marked this as In progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 8 | OCF should test the Fair Elections Program e-filing system periodically to make sure automated controls like flagging ZIP codes outside D.C. and flagging excess contributions are working as intended. | OCF | In progress | OCF reported this recommendation as Implemented. ODCA asked for additional information but has not heard back so we marked this as In progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 9 | OCF should adjust requirements, working with the Council if necessary, so that matching is available only when residential addresses within D.C. are supplied (i.e. street address, not P.O. Box). | OCF | Not yet started | OCF stated P.O. Boxes are not acceptable for matching funds, however our report found 11 instances of either a P.O. Box or no address for the contributor submitted.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 10 | OCF should review audit records of the Fair Elections Program e-filing system for indications of inappropriate or unusual activity, at a defined frequency, and report findings to designated OCF personnel. | OCF | Not yet started | OCF reported this recommendation as Implemented. ODCA asked for additional information but has not heard back so we marked this as In progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 11 | OCF should ensure that the Fair Elections Program e-filing system is supported by OCF IT personnel who are equipped with experience, training, and supervision to complete or delegate the tasks that are necessary to manage its security and privacy proactively. | OCF | In progress | OCF reported this recommendation as Implemented but also noted revisions to the Fair Elections Program Standard Operating Procedures would be made. We have marked this as In Progress.
Fair Elections Program Was Well-Run but Program Controls Can Be Improved (January 21, 2022) | 12 | When external changes increase the risk associated with following standard operating procedures, OCF should develop temporary procedures that are practical under the circumstances and adequately mitigate all relevant risks, including loss or theft of funds, and ensure they are followed. | OCF | Implemented
Fiscal Year 2020 Annual Report on Advisory Neighborhood Commissions (May 23, 2022) | 3 | The OANC should continue to work with ANCs to strengthen compliance with internal control procedures to protect ANC assets and District resources, which can also improve accountability and public trust. | OANC | Implemented
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 1 | The Office of Neighborhood Safety and Engagement should include the conviction data required by the NEAR Act in all future annual reports on the Pathways program. | ONSE | In progress | ONSE reported that the CJCC declined to provide access to the JUSTIS database and they are in discussions with CSOSA to collect conviction data.
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 2 | The Office of Neighborhood Safety and Engagement should partner with the Department of Employment Services to report longitudinal employment outcomes for Pathways participants using the unemployment insurance tax database maintained by DOES. | ONSE | In progress | ONSE said they are talking with DOES about the possibility of using DOES data.
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 3 | The Office of Neighborhood Safety and Engagement should collect and report data on victimization of Pathways participants, drawing on data from the District's health information exchange and DC Health's Firearm Surveillance Through Emergency Rooms system. | ONSE | In progress | ONSE report the collection has begun via partnerships with VIs at local hospitals and the Office of Gun Violence Prevention.
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 4 | The Office of Neighborhood Safety and Engagement should continue to use any additional funds appropriated by the Mayor and Council not only to increase the number of violence interruption sites, but also to increase the number of violence interrupters per site, focusing on areas with the highest levels of gun violence and homicides. | ONSE | Implemented
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 5 | The Office of Neighborhood Safety and Engagement should direct its violence intervention contractors to ensure that managers and violence interrupters introduce themselves to advisory neighborhood commissioners and that the contractors keep communities informed through meetings of the ANCs, civic associations, resident councils, and MPD Citizens Advisory Councils. | ONSE | Implemented
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 6 | The D.C. government should contract with a criminal justice research organization to evaluate both violence intervention programs, comparing outcomes in program sites to neighborhoods that are closely matched in demographics and initial levels of crime. This research should analyze not only the end outcomes but also the activities and intermediate outcomes that are part of the program model. | EOM (OCA) | In progress
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 7 | The Mayor and Council should use an independent research study of the District’s violence intervention programs to assess whether and how to integrate or merge the programs run by the Office of Neighborhood Safety and Engagement and the Office of the Attorney General. | EOM (OCA) | In progress
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 7 |  | DC Council
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 8 | The Council should amend the NEAR Act to (a) delete the requirement for a DC Health Office of Violence Prevention and Health Equity, and (b) shift responsibility to develop and implement a public health strategy to combat the spread of violence to the Office of the City Administrator. | DC Council | Not yet started
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 9 | The Council should amend the NEAR Act to state that the Office of Victim Services and Justice Grants shall oversee a citywide network of hospital-based violence intervention programs targeted at Level 1 and Level 2 trauma centers that operate during hours specified in grant agreements and should provide sufficient resources for the services. | DC Council | Not yet started
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 10 | The Office of Victim Services and Justice Grants should modify the existing key performance indicator on client enrollment to reflect the number of victims who accept hospital-based violence intervention services divided by the number of patients treated at the hospital for community-based violence. | OVSJG | Implemented
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 11 | The Office of Victim Services and Justice Grants should supplement the client enrollment key performance indicator by including results of key program activities in its annual performance plans and reports such as (i) percentage of clients demonstrating improvements in mental health, (ii) percentage of clients who were awarded crime victims’ compensation benefits, or (iii) percentage of clients enrolled in health insurance. | OVSJG | Not yet started
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 12 | The Metropolitan Police Department should comply with the law by establishing the Community Crime Prevention Team program, in partnership with the Department of Behavioral Health and the Department of Human Services. | MPD | In progress
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 13 | The Office of Victim Services and Justice Grants should include performance measures and targets for the private security camera program in its annual performance plans, as well as data on actual performance in its annual performance reports. | OVSJG | In progress | OVSJG reported this as Implemented however they are waiting final approval for three new private security camera performance measures to be included in the performance plan.
NEAR Act Violence Prevention and Interruption Efforts: Opportunities to Strengthen New Program Models (June 7, 2022) | 14 | The Council should add the Supplemental Nutrition Assistance Program to the list of programs that qualify residents to receive security camera program vouchers. | DC Council | In progress | The Committee on Judiciary and Public Safety reported there is legislation in Committee relating to the security camera rebate and is incorporating this recommendation in that legislation. A draft committee print to Bill 25-345 was circulated in January 2024.
36 Fired MPD Officers Reinstated; Receive $14 Million in Back Pay (October 6, 2022) | 1 | When the D.C. Council acts on permanent legislation to codify the removal of discipline from collective bargaining as approved in the Comprehensive Policing and Justice Reform Congressional Review Emergency Amendment Act of 2022, legislators should make clear in D.C. Code or report language that they are eliminating arbitration and assigning additional responsibilities to the Office of Employee Appeals. This action will help reduce the risk of returning poor performers to the force while protecting the due process rights of District employees. | DC Council | Not yet started
36 Fired MPD Officers Reinstated; Receive $14 Million in Back Pay (October 6, 2022) | 2 | To minimize subjectivity over the severity of discipline for misconduct and ensure discipline decisions reflect current policy, the D.C. Council should codify the MPD table of penalties with due consideration given to recommendations from the Chief of Police. | DC Council | Not yet started
36 Fired MPD Officers Reinstated; Receive $14 Million in Back Pay (October 6, 2022) | 3 | The Mayor and Council should direct the review and amendment of MPD General Order GO-120, 6 DCMR § 1001.5, and/or D.C. Code § 5–133.06 to address the inconsistency between General Orders and D.C. Code that has resulted in overturned terminations. | EOM (OCA) | Implemented | The Office of the City Administrator, on behalf of the Mayor, reported this recommendation as No longer applicable and noted MPD published General Order 120.21 in November 2022. The Committee on Judiciary and Public Safety reported they are evaluating this recommendation. ODCA believes this has been Implemented.
36 Fired MPD Officers Reinstated; Receive $14 Million in Back Pay (October 6, 2022) | 3 |  | DC Council
36 Fired MPD Officers Reinstated; Receive $14 Million in Back Pay (October 6, 2022) | 4 | MPD should comply with statutory requirements on timely action in discipline matters, provide evidence sufficient to support any MPD appeals, and recommend clarification to the requirements to the extent needed. | MPD | Implemented | MPD provided examples of timely reinstatements.
36 Fired MPD Officers Reinstated; Receive $14 Million in Back Pay (October 6, 2022) | 5 | While arbitration remains an option, the Council should enact time limits on referring new cases for arbitration applicable both to MPD and sworn members of the department and their collective bargaining unit consistent with the 30-day limit now in place for cases referred to the Office of Employee Appeals. | DC Council | Not yet started
36 Fired MPD Officers Reinstated; Receive $14 Million in Back Pay (October 6, 2022) | 6 | To reduce the cost to the D.C. government of lengthy appeals, MPD should work with the Office of the Attorney General (OAG) to develop written criteria for whether to appeal termination cases including a financial risk assessment. | MPD | In progress
36 Fired MPD Officers Reinstated; Receive $14 Million in Back Pay (October 6, 2022) | 7 | MPD should stop ignoring court orders and reinstate terminated employees in a timely fashion when so ordered. | MPD | Implemented
36 Fired MPD Officers Reinstated; Receive $14 Million in Back Pay (October 6, 2022) | 8 | As part of the required annual report on misconduct and grievances, MPD should analyze the disciplinary data from the prior year to assess trends in misconduct and guide initiatives that reduce misconduct. | MPD | In progress
Multiple Failures in Department of General Services Management of Work Orders (November 28, 2022) | 1 | DGS should explore options for implementation of an inventory management system that integrates with the District's CMMS. | DGS | In progress
Multiple Failures in Department of General Services Management of Work Orders (November 28, 2022) | 2 | DGS should implement a robust supervisory review of work orders. This review should provide an independent assessment of the accuracy and reasonableness of data entered for the work order. | DGS | Implemented
Multiple Failures in Department of General Services Management of Work Orders (November 28, 2022) | 3 | We recommend DGS begin tracking preventative maintenance activities in a CMMS. This should include the import of manufacturer recommended maintenance schedules as well as warranty requirements for each asset. | DGS | In progress
Multiple Failures in Department of General Services Management of Work Orders (November 28, 2022) | 4 | As part of a broader shift from reactive maintenance to proactive asset management, we also recommend DGS begin efforts to inventory individual assets, so that maintenance tasks can be applied to individual assets, instead of only the building/location. | DGS | In progress | DGS reported this as implemented. While we do believe they have begun this recommendation DGS also notes their plan to continue to add more service types.
Multiple Failures in Department of General Services Management of Work Orders (November 28, 2022) | 5 | Understanding that capturing an inventory of all assets will require significant effort, we recommend DGS begin with inventory of all new critical assets installed in the District. DGS should also identify other critical assets currently in operation to be inventoried. | DGS | In progress | DGS reported this as implemented. While we do believe they have begun this recommendation DGS also noted their plan to finalize a maintenance module that will track all assets and maintenance activities.
Multiple Failures in Department of General Services Management of Work Orders (November 28, 2022) | 6 | We recommend DGS coordinate with the CMMS provider or implementation partner to assess the cause of the missing work order history information. After identification of the cause, a remedy should be implemented to prevent the future loss or mis-capture of this critical information. | DGS | In progress | DGS reported they have extended the length of time work order data can be retrieved by adding additional storage. ODCA believes the additional storage along with continued monitoring to ensure the preservation of work order data will resolve the issue.
Multiple Failures in Department of General Services Management of Work Orders (November 28, 2022) | 7 | We recommend DGS add dashboard and/or reporting capabilities to the CMMS that will allow supervisors to view open work orders that are noncompliant with the SLA. | DGS | Not yet started | DGS indicated comprehensive work order dashboards have been developed and implemented since Fiscal Year 2019. ODCA's report notes that by adding dashboard and/or capabilities for supervisors would help provide supervisors with knowledge of current assigned SLA statuses when assigning new work orders.
Multiple Failures in Department of General Services Management of Work Orders (November 28, 2022) | 8 | To facilitate additional accountability, we recommend DGS consider associating work order responsiveness to performance evaluations. | DGS | In progress
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 1 | The D.C. Council should amend the legislation to require the provision of resources and staff support, as well as clear authority for access to laboratory records to enable the SAB to perform its oversight functions. | DC Council | Not yet started
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 2 | The D.C. Council and the Mayor, as part of the annual budget process, should allocate sufficient administrative and financial resources for the SAB to perform its oversight functions. | DC Council | Not yet started | The Executive reported this recommendation as In progress and noted that DFS supports the SAB in the planning and coordination of their quarterly meetings as required. The Council Committee on Judiciary and Public Safety indicated they are evaluating this recommendation and researching other jurisdiction's models for forensic lab support. We have marked this recommendation as Not yet started.
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 2 |  | EOM (OCA)
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 3 | The Executive should develop policies and procedures for preparing Stakeholder Council meeting agendas, discussions, and action items. | EOM (OCA) | In progress
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 4 | To facilitate representation by stakeholder agencies, the D.C. Council should amend the legislation to allow Stakeholder Council members to be represented in the meetings by designees when they are unable to attend. | DC Council | Not yet started
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 5 | The D.C. Council should require DFS to rewrite the regulations to conform with D.C. Code and ensure that the SAB receives all allegations of professional negligence, misconduct, or misidentification or other testing error that occurs in the provision of forensic science services including all internal and external complaints. | DC Council | Not yet started
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 6 | The D.C. Council should amend legislation to define the term “immediately”. | DC Council | Not yet started
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 7 | The Executive should ensure that DFS leadership fosters and maintains agency independence by: *Improving and maintaining ongoing communication and cooperation with its customers. *Monitoring and assisting DFS in resolving serious disagreements with customers including, specifically, USAO and OAG. | EOM (OCA) | In progress
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 8 | DFS’s Director should provide training for the management team on effective customer service including how to improve DFS’s responsiveness to customers’ needs and the overall relationship and communications with all customers. | DFS | Implemented
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 9 | DFS should develop and implement procedures for monitoring and maintaining the designated email account for receiving complaints. | DFS | Implemented
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 10 | DFS should record any allegation of misconduct as a complaint, investigate the complaint in accordance with its policies and procedures and immediately report it to the SAB. | DFS | In progress | DFS reported this recommendation as Implemented and indicated the Office of the General Counsel would report to the SAB at a regularly scheduled SAB meeting. The SAB website shows meetings to occur generally on a quarterly basis. Absent more immediate indication to the SAB, we have marked this recommendation as In progress.
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 11 | DFS should provide training to the entire staff on DFS’s processes, policies, and procedures including the complaint process to ensure adherence to established laboratory protocols. | DFS | Implemented
D.C. Forensics Lab Fails to Achieve Independence (December 1, 2022) | 12 | DFS should create and maintain case files for all complaints. | DFS | Implemented
*DSLBD received notification of the recommendation as a part of recommendation compliance report.
** MPD Implmented in November, 2022.